## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information | [12 empty] | Wexford Construction
ESC File No. | C10E001A |  | Project Name: |  | Sonata Green | [7 empty] | JL Murtagh
NPDES Id. No. | NMR1005FW |  | Location: |  | Tree Line Ave. and Universe Blvd. | [5 empty] | Sonata Green Owner, LLC; John Murtagh |  | 505-259-3397
2025-02-07 |  | Owner |  |  |  | Contractor |  |  |  |  | 702-376-5287 |  | JL@wcinm.com
Operator |  | Sonata Green, LLC. |  |  |  | Wexford Construction
Contact name & title |  | John Murtagh |  |  |  | JL Murtagh |  |  |  |  | Tim Slatunas
e-mail |  | jmurtagh@wcinm.com |  |  |  | JL@wcinm.com
Contact Phone # |  | 702-376-5287 |  |  |  | 505-259-3397 |  |  |  |  | Mike Webb | mike@enviroworksforyou.com | 505-331-6101
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 1:30pm |  |  |  |  | Rain
Construction Phase: |  | verticals | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 65 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2024-11-07 |  |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Washout - There was concrete washout on the ground from a leaking washout container in violation of CGP Part 2.3.4. Required mitigation: Direct wash water into a leak-proof container or a leak-proof and lined pit designed so no overflows can occur due to inadequate sizing or precipitation per CGP Part 2.3.4. Do not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground. Remove and dispose of hardened concrete waste consistent with your handling of other construction wastes. | [9 empty] | 2021-05-03
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | yes | Latest report Date: |  | 2025-02-05
Notes:
The SWPPP was in the construction office in Apartment 105 on Tree Line Ave NW.
6601 Tree Line Ave NW #105
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English 505-924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action