## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information | [12 empty] | Wexford Construction
ESC File No. | C10E001A |  | Project Name: |  | Sonata Green | [7 empty] | JL Murtagh
NPDES Id. No. | NMR1003AC |  | Location: |  | Tree Line Ave. and Universe Blvd. | [5 empty] | Sonata Green Owner, LLC; John Murtagh |  | 505-259-3397
2023-12-27 |  | Owner |  |  |  | Contractor |  |  |  |  | 702-376-5287 |  | JL@wcinm.com
Operator |  | Sonata Green, LLC. |  |  |  | Wexford Construction
Contact name & title |  | John Murtagh |  |  |  | JL Murtagh |  |  |  |  | Tim Slatunas
e-mail |  | jmurtagh@wcinm.com |  |  |  | JL@wcinm.com
Contact Phone # |  | 702-376-5287 |  |  |  | 505-259-3397 |  |  |  |  | Mike Webb | mike@enviroworksforyou.com | 505-331-6101
COA Inspector |  | James Hughes |  |  |  | Start/End Time: |  | 2:45pm |  |  |  |  | Rain
Construction Phase: |  | Grading | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 50 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2023-12-23 |  |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | SWPPP map not up-to-date, offsite disturbed areas north and sout of this site are part of this common plan of development. Required Mitigation: Offsite limits of disturbance and a stabilization specification must be added to the map. The SWPPP, including the Map, the NOI, Self Inspection Reports and Corrective Action Reports, must be kept up-to-date per CGP 7.1 and available on-site per CGP 4.7.3, 5.4.3 and 7.3. | [9 empty] | 2021-05-03
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2023-11-29
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | James Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action