## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C11E004 |  | Project Name: |  | Rosa Parks Stockpile Yard
NPDES Id. No. | NMR100501 |  | Location: |  | Rosa Parks and Kimmick
2024-07-18 |  | Owner |  |  |  | Contractor
Operator |  | Steve.Metro@wilsonco.com NMR100504 |  |  |  | Guzman Construction
Contact name & title |  | Altagracia Pena NMR100501 |  |  |  | Lutita Pena, NMR1004ZB
e-mail |  | lupita@guzmancs.com |  |  |  | lupita@guzmancs.com
Contact Phone # |  | 505-341-8591 |  |  |  | AP452-0663 SM280-4553
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 2pm |  |  |  | Rain
Construction Phase: |  | Stockpiles | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 90 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-06-30 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The perimeter silt fence needs maintenance in vilation of CGP Part 2.1.4. Required mitigation: Ensure all stormwater controls are maintained and remain in effective operating condition during the permit coverage and are protected from activities that would reduce their effectiveness per CGP Part 2.1.4.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2024-07-17
Notes: | QR code for SWPPP and Inspection reports.
Prior violations for Posting, SWPPP, BMPs, and stabilization
Weeds are becoming overgrown again and exceeding the 4" width and 4" height allowed by City Ordinance 9-8-4.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action