## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C11E004 |  | Project Name: |  | Rosa Parks Stockpile Yard
NPDES Id. No. | NMR100501 |  | Location: |  | Rosa Parks and Kimmick
4/11/2025, 5/1/2025 |  | Owner |  |  |  | Contractor
Operator |  | Steve.Metro@wilsonco.com NMR100504 |  |  |  | Guzman Construction
Contact name & title |  | Altagracia Pena NMR100501 |  |  |  | Lupita Pena, NMR1004ZB
e-mail |  | lupita@guzmancs.com |  |  |  | lupita@guzmancs.com
Contact Phone # |  | 505-341-8591 |  |  |  | AP452-0663 SM280-4553
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 2pm |  |  |  | Rain
Construction Phase: |  | Stockpiles and construction support | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 70 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-04-20 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The perimeter silt fence needs replacement in violation of CGP Part 2.1.4. Required mitigation: Ensure all stormwater controls are maintained and remain in effective operating condition during the permit coverage and are protected from activities that would reduce their effectiveness per CGP Part 2.1.4.
2 | The SWPPP and inspection reports were unavailable (Same as paper) at the time of inspection in violation of CGP Parts 4.7.3 and 7.3 Require mitigation: You must keep a copy of your SWPPP and all inspection reports at the site or at an easily accessible location so that they can be made immediately available at the time of an on-site inspection per CGP Parts 4.7.3 and 7.3
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes: | QR code for SWPPP and Inspection reports.
Prior violations for Posting, SWPPP, BMPs, and stabilization
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action