## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C11E004 |  | Project Name: |  | Rosa Parks Stockpile Yard
NPDES Id. No. | NMR100501 |  | Location: |  | Rosa Parks and Kimmick
2025-08-14 |  | Owner |  |  |  | Contractor
Operator |  | Steve.Metro@wilsonco.com NMR100504 |  |  |  | Guzman Construction
Contact name & title |  | Altagracia Pena NMR100501 |  |  |  | Lupita Pena, NMR1004ZB
e-mail |  | lupita@guzmancs.com |  |  |  | lupita@guzmancs.com
Contact Phone # |  | 505-341-8591 |  |  |  | AP452-0663 SM280-4553
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 2pm |  |  |  | Rain
Construction Phase: |  | Stockpiles and construction support | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 90 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-07-03 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | None
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2025-07-30
Notes: | QR code for SWPPP and Inspection reports.
Prior violations for Posting, SWPPP, BMPs, and stabilization
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action