## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C11E004 |  | Project Name: |  | Rosa Parks Stockpile Yard
NPDES Id. No. | NMR1004ZB |  | Location: |  | Rosa Parks and Kimmick
2022-08-25 |  | Owner |  |  |  | Contractor
Operator |  | Steve.Metro@wilsonco.com NMR100504 |  |  |  | Guzman Construction
Contact name & title |  | Altagracia Pena NMR100501 |  |  |  | Lutita Pena, NMR1004ZB
e-mail |  | lupita@guzmancs.com |  |  |  | lupita@guzmancs.com
Contact Phone # |  | 505-341-8591 |  |  |  | AP452-0663 SM280-4553
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 1:30-2pm |  |  |  | Rain
Construction Phase: |  | Staging | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Cloudy |  | Temperature: ~ |  |  | 75 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2022-07-24 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | none - Previous violations (SWPPP, NOIs, BMPs, Posting, and Stabilization has been provided for Tracts 1-3 of Block 6) had been mitigated. | [9 empty] | 2021-05-03
2 | [10 empty] | 2021-05-31
3 | [10 empty] | 2021-06-28
4 | [10 empty] | 2021-07-06
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | n/a | Latest report Date: |  | none
Notes:
The SWPPP is in Tom Meier's pickup onsite Ph 453-8625 thomas.Meier02@icloud.com. Tom is Guzman's DA. Tracts 1-5 Block 6 are entirely covered by recent land disturbing activities. There is also a large area of land disturbance on the portion of Tract 1 Blk 2. The site is mostly inactive, with the exception of water trucks going back and forth between the hydrants on the east and La Cuentista III on the west.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action