## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
Project Name: |  | Fountain Hills Assisted Living
Location: |  | 4551 Vista Fuente Rd. NW
Site Contact Name & Agency |  | Shawn Biazar - SBS |  |  |  | ESC File No. | C12E003B8
|  | aecllc@aol.com |  |  |  | NPDES Id. No. | NMR1002DD
Inspection Date: |  | 2020-08-18 | Start/End Time: |  | 10:15/10:45AM
CoA Stormwater Inspector: |  |  | Doug Hughes | [9 empty] | Rain
Construction Phase: |  | Foundation | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event |  | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  |  | Temperature: ~ |  |  | 84 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [8 empty] | 2020-08-01 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Holes in silt fence on low side of site near roundabout needs maintenance.
2 | Fill has been stockpiled on the adjacent lot without approval from the City. ESC Plan and NOI required.
***Please provide latest SWPPPP nself-inspection report
Yes
2.1 | Discharge off site? (Y/N) |  |  | Yes | [7 empty] | No
4 | Self Inspection Reports |  |  | requested |  | Latest report Date: |  | 2020-01-17
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
|  | jhughes@cabq.gov |  |  |  |  | 2020-08-18

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action