## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C12E003B8 |  | Project Name: |  | Fountain Hills Assisted Living
NPDES Id. No. | NMR1002DD |  | Location: |  | 4551 Vista Fuente Rd. NW | [5 empty] | Michael Montoya |  | Novus Properties LLC |  | michael@cginm.com
2021-07-16 |  | Owner |  |  |  | Contractor
Operator |  | JB2C, LLC.
Contact name & title |  | Biju Cherian |  |  |  | Shawn Biazar
e-mail |  | bijucherian@hotmail.com |  |  |  | aecllc@aol.com
Contact Phone # |  | 505-264-8120 |  |  |  | 505-804-5013
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 11:00 AM-11:15 AM | [5 empty] | Rain
Construction Phase: |  | Building construction | [11 empty] | Clear/ Windy
Type of Inspection: |  |  |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 85 |  |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-07-15 |  |  |  |  | 2021-02-22 |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [13 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28 | 2021-05-03
1 | Silt fence in need of repair. Repair/replace silt fence and maintain all erosion and sediment controls. | [9 empty] | 2021-05-03
2 | Sediment in street/sidewalk. Remove trackout and sediment from the street/sidewalk daily.
3 | Sediment accumulation at inlet protection. Remove any sediment accumulated at the inlet/mulch sock daily.
4 | Washout on the ground. Direct any wash water into a leak-proof container and dispose of properly.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2020-09-11
Notes: | Superintendent not on site during this inspection.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action