## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C12E003B8 |  | Project Name: |  | Fountain Hills Assisted Living
NPDES Id. No. | NMR1002DD |  | Location: |  | 4551 Vista Fuente Rd. NW | [5 empty] | Michael Montoya |  | Novus Properties LLC |  | michael@cginm.com
2021-11-02 |  | Owner |  |  |  | Contractor
Operator |  | JB2C, LLC.
Contact name & title |  | Biju Cherian |  |  |  | Shawn Biazar
e-mail |  | bijucherian@hotmail.com |  |  |  | aecllc@aol.com
Contact Phone # |  | 505-264-8120 |  |  |  | 505-804-5013
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 8:30 | [5 empty] | Rain
Construction Phase: |  | Building occupied, offsite partially mulched but not Stabilized. | [11 empty] | Clear/ Windy
Type of Inspection: |  |  |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 39 |  |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-10-01 |  |  |  |  | 2021-02-22 |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [13 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28 | 2021-05-03
1 | The building is occcupied, onsite landscaping complete, but the stabilization of the offsite stockpile area doesn't satisfy the criteria in CGP2.2.14.b. The stockpile is gone now. The sloped portion of the offsite area has been mulched, but the mulch won't last 3 years, so it only provides temporary cover per CGP2.2.14.a. The flat area on top of the slope is still bare dirt and is unprotected. Permit coverage remains in effect until the ofsite area meets the Final Stabiilization criteria (2.2.14.b) so the coverage must be posted for safe public viewing, self-inspectrion reports must continue and the up-to-date SWPPP must be available onsite. | [9 empty] | 2021-05-03
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2020-09-11
Notes: | Superintendent not on site during this inspection, site not posted, SWPPP not available.
The offsite disturbed area is inactive.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | James D Hughes 505-924-3420
Jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action