## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C12E003C |  | Project Name: |  | The Learning Experience
NPDES Id. No. | NMR10032L |  | Location: |  | 4580 Nunzio Ave NW
2021-11-04 |  | Property Owner |  |  |  | Contractor
Operator |  | Learning Lab Development PER LLC
Contact name & title |  | Scooter Haynes |  |  |  | RJ Chess
|  | scooter@scmpartners.com |  |  |  | rjchess1@gmail.com
Contact Phone # |  | 505 898-6622 |  |  |  | 362-6184
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 8:15am |  |  |  | Rain
Construction Phase: |  | Landscaping | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 45 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2021-10-01 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The SWPPP is missing the Owner's Certification.
2
Yes
2.1 | Discharge off site? (Y/N) |  |  | No | [6 empty] | No
4 | Self Inspection Reports |  |  | Ok | Latest report Date: |  | 2021-11-04
Notes: | The building and parking lot were complete and Landscaping is underway.
Stabilization is still needed in both the onsite landscape areas and in the adjacent areas of
land-disturbing activities. Deligation of Authority to Inspections plus is signed in the SWPPP.
Self inspection reports have been e-mailed to Owner and City. No sediment offsite.
No washout or waste present.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action