## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C12E003C |  | Project Name: |  | The Learning Experience
NPDES Id. No. | NMR10032L |  | Location: |  | 4580 Nunzio Ave NW
2020-09-25 |  | Property Owner |  |  |  | Contractor
Operator |  | Learning Lab Development PER LLC
Contact name & title |  | Scooter Haynes
scooter@scmpartners.com
Contact Phone # |  | 505 898-6622
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 10:50/11:30AM |  |  |  | Rain
Construction Phase: |  | Earthwork | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 76 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [11 empty] | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The ESC Plan is still not approved and won't be until the G&D Plan is. The G&D Plan was re-submited to Hydrology 9/18/2020 and is still in review.
2 | The Construction Entrance is still missing. Recent access has been through the adjacent Construction Site , Smiles For Kids, and that trackout pad was removed and replaced with dirt. Both Construction entrances must be reestablished and maintained.
Yes
2.1 | Discharge off site? (Y/N) |  |  | No | [6 empty] | No
4 | Self Inspection Reports |  |  |  | Latest report Date: |  | 2020-09-23
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action