## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C12E003C |  | Project Name: |  | Learning Experience | [5 empty] | 4580 Nunzio Ave NW
NPDES Id. No. | NMR10032L |  | Location: |  | 4580 Nunzio Ave. NW | [5 empty] | scooter@scmpartners.com
2021-05-07 |  | Owner |  |  |  | Contractor
Operator |  | Learning Lab Development PER LLC | [8 empty] | dustinfewell@icloud.com
Contact name & title |  | Scooter Haynes |  |  |  | Dustin Fewell
e-mail |  | scooter@scmpartners.com |  |  |  | dustinfewell@icloud.com | [5 empty] | 898-6622
Contact Phone # |  | 505-898-6622
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 11:00 AM/11:30 AM |  |  |  |  | Rain
Construction Phase: |  | Building construction | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 77 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-05-03 |  |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Sediment accumulation against the South silf fence. Remove sediment from the silt fence. Maintain sediment control BMPs. | [9 empty] | 2021-05-03
2 | Sediment accumulation at the inlet. Remove sediment and re-position wattle to prevent sediment from entering the inlet.
3
4
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2021-04-20
Notes: | Spoke with superintendent. Cranes are coming in on Tuesday, and the dirt pile on the South
side will be cleared from the fence. No vehicles are parking on site. They are using the adjacent lot
to the South for staging.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action