## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C12E004 |  | Project Name: |  | Kiddie Academy Westside
NPDES Id. No. | NMR100370 |  | Location: |  | 4590 Paradise Blvd. NW
2023-03-06 |  | Owner |  |  |  | Contractor
Operator |  | Azaan Holdings |  |  |  | Snyder Construction
Contact name & title |  | Aleem Hasham |  |  |  | Benny Saiz
e-mail |  | aleemhasham@kiddieacademy.net |  |  |  | bsaiz@snyder-const.com
Contact Phone # |  | 501-256-9687 |  |  |  | 505-263-0961
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 1:30pm |  |  |  |  | Rain
Construction Phase: |  | Building construction | [10 empty] | Clear/ Windy
Type of Inspection: |  | Follow-up |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 62 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2022-12-04 |  |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28 | 2021-05-03
2 | none
3
4
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2022-08-11
Notes:
There still isn't any significant growth of perennial vegitation. The mulch is still OK at 16 months
old. You must continue permit coverage, self-inspections, SWPPP and BMP maintenance until the City determines that the Final Stabilization Criteria CGP2.2.14.c has been satisfied. Then you must remove the BMPs and send documentation of the Final Stabilization to the EPA with a Notice of Termination (NOT) per CGP 8.2 to end your coverage under the CGP. This step is independent of the Certificate of Occupancy. Please copy me with the documentation and the EPA’s acceptance of the NOT.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action