## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C12E004 |  | Project Name: |  | Kiddie Academy Westside
NPDES Id. No. | NMR100370 |  | Location: |  | 4590 Paradise Blvd. NW
2021-12-02 |  | Owner |  |  |  | Contractor
Operator |  | Azaan Holdings |  |  |  | Snyder Construction
Contact name & title |  | Aleem Hasham |  |  |  | Benny Saiz
e-mail |  | aleemhasham@kiddieacademy.net |  |  |  | bsaiz@snyder-const.com
Contact Phone # |  | 501-256-9687 |  |  |  | 505-263-0961
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 9:30 -10:30 am |  |  |  |  | Rain
Construction Phase: |  | Building occupied, onsite finished, offsite not stabilized, trailer still onsite. | [10 empty] | Clear/ Windy
Type of Inspection: |  | Follow-up |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 45 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-10-01 |  |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28 | 2021-05-03
1 | Permit coverage not posted for safe public viewing.
2 | SWPPP was not up-to-date. The SWPPP map did not show current BMPs. The Operator's signature was missing from thye SWPPP and the inspection reports. The deligation to Snyder doesn't meet the requirements of Appendix I (no third party deligations) and the deligation wasn't signed by the Operator (Snyder signed it). Add operator signatures and up-date the map.
4 | Final stabilization per CGP2.2.14.b required to terminate permit coverage. Continue inspections and BMPs until then. City Std Spec 1012 Native seed and agregate mulch provides immediate final stabilization so permit coverage and inspections can be terminated promptly.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  |  | Latest report Date: |  | 2021-11-04
Notes: | Onsite stabilized, offsite has seed and mulch recently applied.
The SWPPP will be kept inside the building in the office to the left of the entrance.
Inspection frequency can be reduced to once a month if cover satisfies 2.2.14.a.
Cover sediment, posting and SWPPP to be monitored by inspections.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes 505-924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action