## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C13E001 |  | Project Name: |  | Sedona West Apartments
NPDES Id. No. | NMR100596 |  | Location: |  | 9330 Eagle Ranch Rd
2024-05-21 |  | Owner |  |  |  | Contractor
Operator |  | Palindrome Sedona West LLC |  |  |  | Pacificap Construction
Contact name & title |  | Heather Boyd |  |  |  | Ron Samp
e-mail |  | hboyd@palindromecreates.com |  |  |  | rsamp@pacificap.com
Contact Phone # |  | 503-288-6210 |  |  |  | 505-496-5259
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 230pm |  |  |  | Rain
Construction Phase: |  | Verticals, utilities | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 80 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-04-01 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The permit coverage posting was missing from the site in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site per CGP Part 1.5.
2 | SWPPP - The SWPPP has not been certified by the operators in violation of CGP Part 7.2.10. The self inspection reports were not available during the city's inspection in violation of CGP Part 4.7.3. The contractor's (Pacificap) NOI was not included in the SWPPP in violation of CGP Part 7.2.11. Required mitigation: Your signatory must sign and date your SWPPP in accordance with CGP Appendix G, Part G.11. You must keep a copy of all inspection reports at the site or at an easily accessible location so that it can be made immediately available at the time of an on-site inspection per CGP 4.7.3. A copy of your NOI submitted to EPA along with any correspondence exchanged between you and EPA related to coverage under the CGP per CGP Part 7.2.11.
3 | The perimeter silt fence was not installed or had been removed in violation of CGP Part 2.2.3. Stockpiles are located outside the perimeter fencing in violation of CGP Part 2.2.5.b. Required mitigation: Install sediment controls along any perimeter areas of the site that are downslope from any exposed soil or other disturbed areas per CGP Part 2.2.3. Install a sediment barrier along all downgradient perimeter areas of stockpiled soil or land clearing debris per CGP Part 2.2.5.b.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2024-05-17
Notes:
SWPPP is in the Pacificap office in the strip mall adjacent to site.
Concrete waste/washout containers are full.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action