## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C13E001 |  | Project Name: |  | Sedona West Apartments
NPDES Id. No. | NMR100596 |  | Location: |  | 9330 Eagle Ranch Rd
2025-04-23 |  | Owner |  |  |  | Contractor
Operator |  | Palindrome Sedona West LLC |  |  |  | Pacificap Construction
Contact name & title |  | Heather Boyd |  |  |  | Jeffrey Harrison
e-mail |  | hboyd@palindromecreates.com |  |  |  | jharrison@pacificap.com
Contact Phone # |  | 503-288-6210 |  |  |  | 505-249-6053
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 3pm |  |  |  | Rain
Construction Phase: |  | Verticals and interiors | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 70 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-04-20 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | There was litter and construction wastes scattered over the site in violation of CGP Part 2.3.3.e. Required mitigation: On business days, clean up and dispose of waste in designated waste containers and clean up immediately if containers overflow, and if there is litter elsewhere on your site from escaped trash per CGP Part 2.3.3.e.
2 | Sediment is being tracked out of the site onto Eagle Ranch Rd and the access road to the south in violation of CGP Part 2.2.4. Required mitigation: Use appropriate stabilization techniques at all points that exit onto paved roads and implement additional track-out controls as necessary to ensure that sediment removal occurs prior to vehicle exit per CGP Part 2.2.4. Where sediment has been tracked-out from your site onto paved roads, remove the deposited sediment by the end of the same business day in which the track-out occurs. Remove the track-out by sweeping, shoveling, or vacuuming these surfaces.
3 | The self-inspection reports available on-site were not current in violation of CGP Part 4.7.3. Required mitigation: You must keep a copy of all inspection reports at the site or at an easily accessible location so that they can be made immediately available at the time of an on-site inspection per CGP Part 4.7.3.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2025-01-23
Notes:
SWPPP is in the Pacificap office in the strip mall adjacent (SE) to site, between to AAA and Audio Express
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action