## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C13E025F |  | Project Name: |  | Christiansen Oral Surgery
NPDES Id. No. | NMR1007K2 |  | Location: |  | 9378 Valley View Dr NW
2026-02-12 |  | Owner |  |  |  | Contractor - NMR1007JW
Operator |  | MFJ LLC |  |  |  | Trinity Construction
Contact name & title |  | Jennifer Christiansen |  |  |  | Eric Tidmore
e-mail |  | jenchristiansen505@gmail.com |  |  |  | eric@trinitynm.com
Contact Phone # |  | 505-246-6006 |  |  |  | 505-858-9960
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 11am |  |  |  | Rain
Construction Phase: |  | verticals | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 65 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2026-01-08 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | Your permit coverage posting was missing from the site in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to your construction site per CGP Part 1.5. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site, and it must use a font large enough to be readily viewed from a public right-of-way.
2 | The SWPPP and inspection reports were not available on-site during the inspection in violation of CGP Parts 4.7.3 and 7.3. Required mitigation: You must keep a copy of the current SWPPP and all inspection reports at the site or at an easily accessible location so they can be made immediately available at the time of an on-site inspection per CGP Parts 4.7.3 and 7.3.
3 | There was a large area of concrete washout on bare ground in violation of CGP Part 2.3.4. Required mitigation: Direct wash water into a leak-proof container or a leak-proof and lined pit designed so no overflows can occur due to inadequate sizing or precipitation per CGP Part 2.3.4. Do not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground.
4 | The porta-potty is not anchored in violation of CGP Part 2.2.3.f. Required mitigation: Position portable toilets so they are secure and will not be tipped or knocked over, and are located away from receiving waters, storm drain inlets, and constructed or natural drainage features per CGP Part 2.3.3.f.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
The superintendent was not on-site during the inspection.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action