## 26.03.13Form
City of Albuquerque | [7 empty] | Inspection: | Weather: | Violation: | Reports: | Discharge: | ROW: | Yes/No/NA
Stormwater, Erosion, and Sediment Control | [7 empty] | Inspection | Weather | Violation | Reports | Discharge | ROW Type | Yes/No/NA
Construction Site Inspection Report | [13 empty] | Yes
General Information | [7 empty] | Pre-Construction | Ice | None | Yes | Shadow | Other | No
ESC File #: |  | C13E025F |  | Project Name: | Christiansen Oral Surgery |  |  | Routine | Hail | NOI | No | Yes | Sidewalk | N/A
ABQ-PLAN #: |  | SWQ-2025-00055 |  | Project Address: | 9378 Valley View Dr NW |  |  | Follow-up | Snow | Posting | Requested | No | Street
NPDES ID #: |  | NMR1007K2 |  | Inspection Type: | Routine |  |  | 311/Complaint | Clear | SWPPP | Out-of-date |  | Storm Drain Inlet
2026-04-01 |  | Owner |  |  | Contractor |  |  | Storm Event | Rain | BMPs | Unsigned |  | Drainage Ditch
Operator: |  | MFJ LLC |  |  | Trinity Construction |  |  | Post Storm Even >0.25" | Clear/Windy | Sediment |  |  | Arroyo
Contact Name: |  | Jennifer Christiansen |  |  | Eric Tidmore |  |  |  | Windy | Washout |  |  | Private Property
Contact e-mail: |  | jenchristiansen505@gmail.com |  |  | eric@trinitynm.com |  |  |  | Cloudy | Litter |  |  | N/A
Contact Phone: |  | 505-246-6006 |  |  | 505-858-9960 |  |  |  | Sleet | Porta-potty
COA Inspector: |  | Chancellor English |  | Date of Inspection: | 2026-04-01 | Time of Inspection: | 10am |  |  | Stabilization
NPDES Posting? |  | Yes | SWPPP? | Yes | Notice of Intent? | Yes
Self-Inspection Reports? |  |  | Yes | Date of last report: | 2026-03-17
Weather during inspection: |  |  | Cloudy | Estimated date of last storm 0.25" or greater: |  | 2026-01-08 | Snow
Temperature: ~ |  | 53 | Construction Phase: | Verticals, curbs
Discharge off-site? |  | No | ROW: | N/A
Item # | Violation Category | Deficiency/Corrective Action
1 | SWPPP | The owner has not certified the SWPPP and inspection reports in violation of CGP Parts 4.7.2 and 7.2.10. Required mitigation: The SWPPP and each inspection report must be signed by the operator's signatory in accordance with CGP Appendix G, Part G.11 per CGP Parts 4.7.2 and 7.2.10.
Notes:
Hunter Tidmore is the superintendent (Trinity Construction) and had the SWPPP available on-site.
The CGP posting and silt fence along Valley View Dr have been temporarily removed for utility work and will be reinstalled when completed.
All other previously reported violations have been mitigated.
City of Albuquerque Stormwater Inspector Signature and date:
Contact information: Chancellor English (505) 924-3325
cenglish@cabq.gov

## Page 2
City of Albuquerque
Stormwater, Erosion, and Sediment Control
Construction Site Inspection Report - Page 2
General Information
ESC File #: |  | C13E025F |  | Project Name: | Christiansen Oral Surgery
ABQ-PLAN #: |  | SWQ-2025-00055 |  | Project Address: | 9378 Valley View Dr NW
NPDES ID #: |  | NMR1007K2 |  | Inspection Type: | Routine
COA Inspector: |  | Chancellor English |  | Date of Inspection: | 2026-04-01 | Time of Inspection: | 10am
Item # | Violation Category | Deficiency/Corrective Action
1 | Violation
2 | NOI
3 | Posting
4 | SWPPP
5 | BMPs
6 | Sediment
7 | Washout
8 | Litter
9 | Porta-potty
10 | Stabilization
11
12
13
14
15
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
Contact information: Chancellor English (505) 924-3325
cenglish@cabq.gov
pg 2