## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information | [10 empty] | NMR10023E
ESC File No. | C17E119 |  | Project Name: |  | Horizon Village | [5 empty] | 8814 Horizon
NPDES Id. No. | NMR10023F |  | Location: |  | 8814 Horizon Blvd.
2024-12-11 |  | Owner |  |  |  | Contractor |  |  |  |  | Inspections Plus
Operator |  | Stillbrooke Homes
Contact name & title |  | Chris Kelsey
e-mail |  | ckelsey@stillbrooke.com
Contact Phone # |  | 505-858-1800
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 11:45am |  |  |  | Rain
Construction Phase: |  | Facades, landscaping | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 45 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2024-11-07 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Your permit coverage posting information was missing in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site per CGP Part 1.5. | [9 empty] | 2021-05-03
2 | The self-inspection reports were not up-to-date in violation of CGP Part 4.7.3. The SWPPP Map is missing in violation of CGP Part 7.2.4. Required mitigation: You must keep a copy of all inspection reports at the site or at an easily accessible location the that it can be made immediately available at the time of an on-site inspection per CGP Part 4.7.3. Include a legible map, or series of maps, showing boundaries, construction activities, discharge points, BMPs, any potential pollutants, etc. per CGP Part 7.2.4. | [9 empty] | 2021-05-31
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | yes | Latest report Date: |  | 2022-05-25
Notes:
SWPPP was located in box on back of posting sign.
Construction on all but 6 lots (Lots 3-8) is complete.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action