## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information | [10 empty] | NMR10023E
ESC File No. | C17E119 |  | Project Name: |  | Horizon Village | [5 empty] | 8814 Horizon
NPDES Id. No. | NMR10023F |  | Location: |  | 8814 Horizon Blvd.
2022-06-22 |  | Owner |  |  |  | Contractor |  |  |  |  | Inspections Plus
Operator |  | Stillbrooke Homes
Contact name & title |  | Chris Kelsey
e-mail |  | ckelsey@stillbrooke.com
Contact Phone # |  | 858-1800
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | none |  |  |  | Rain
Construction Phase: |  | vertical 7 units only the rest is vacant | [9 empty] | Clear/ Windy
Type of Inspection: |  |  |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Rain |  | Temperature: ~ |  |  | 82 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2022-03-31 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | none | [9 empty] | 2021-05-03
2 | SWPPP was dripping wet and couldn’t be inspected. Replace if necessary and make sure NOI, CGP, and Corection reports are up-to-date! | [9 empty] | 2021-05-31
3
4
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | n/a | Latest report Date: |  | 2022-06-20
Notes:
Only 7 houses vertical, the rest is inactive. The south duplex looks complete though not occupied yet. Washout had been picked up from ground and disposed, but washout containers need replaced.
SWPPP in lockbox but was dripping wet. and couldn’t be inspected
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action