## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C18E074A |  | Project Name: |  | Paseo Nuevo Parking lot
NPDES Id. No. | NMR1002WY |  | Location: |  | 6321 Holly
2021-05-03 |  | Owner |  |  |  | Contractor |  |  |  |  | Skip Skarsgard |  | 505-262-2323
Operator |  | Paseo Nuevo Limited Co.
Contact name & title |  | Skip Skarsgard | [8 empty] | Jeremy Zak | 505-362-1840 |  |  | Cassandra Durkin' <cassandra@inspectionsplus.com>
e-mail |  | skip@ziarisingnm.com
Contact Phone # |  | 505-262-2323 |  |  |  | 505-362-1840 |  |  |  |  | jason@skarsco.com |  | Superintendent
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 11:10 AM/11:15 AM | [5 empty] | Rain
Construction Phase: |  | paving, stabilization | [11 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | cloudy |  | Temperature: ~ |  |  | 66 |  |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-04-28 |  |  |  |  | 2021-02-22 |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [13 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Holes in silt fences. Silt fences are not properly installed. Repair/replace and maintain silt fences and other sediment BMPs (mulch socks).
2 | No posting of permit coverage. Post notice of permit coverage in a clearly visibile to the public location.
3
4
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2020-11-03
Notes: | No activity on site.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action