## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
Project Name: |  | Southwest Corner of Alameda and Louisiana
Location: |  | Alameda & Louisiana |  |  |  | ESC File No. | C18E075 |  | NPDES Id. No. | unknown
Site Contact Name & Agency |  | unknown |  |  |  | Phone: (o)
Phone: (m)
Owner |  | unknown |  |  |  | Phone: (o)
Owner's e-mail | [5 empty] | Phone: (m)
Inspection Date: |  | 2020-08-24 | Start/End Time: |  | 1030/1050hrs
CoA Stormwater Inspector: |  |  | Timothy E. Sims | [9 empty] | Rain
Construction Phase: |  | earthwork | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event |  | Post Storm Event >0.25" |  | x | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  |  | Temperature: ~ |  |  | 82* |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [8 empty] | 2020-07-25 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Provide approved NPDES posting for site.
2 | Provide SWQ approval
3 | Install BMP's per approved SWPPP design.
4 | Silt fence requires maintenance
5 | trackout pad needs to be installed.
6 | Please provide latest SWPPP self-inspection report.
Yes
2.1 | Discharge off site? (Y/N) |  |  | No | [7 empty] | No
4 | Self Inspection Reports |  |  | requested |  | Latest report Date: |  | not on file
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Timothy E. Sims - (505) 803-6155
|  | tsims@cabq.gov |  |  |  |  | 2020-08-24

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action