## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C18E075 |  | Project Name: |  | Sevano Place Subdivision
NPDES Id. No. | NMR10039R & 39X |  | Location: |  | 6300 Alameda Blvd NE
2020-09-21 |  | Property Owner |  |  |  | Contractor
Operator |  | Sevano LLC & Clearbrook Investments |  |  |  | E2RC
Contact name & title |  | Shakeel Rizve & Chris Kelsey |  |  |  | Kelly Fetter
e-mail |  | shaky1424@yahoo.com; ckelsey@stillbrook.com |  |  |  | kfetter@e2rc.com
Contact Phone # |  | 315-6563 & 585-1800 |  |  |  | o 867-4040ext 102
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 2pm |  |  |  | Rain
Construction Phase: |  | Grading | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 76 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [11 empty] | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Self-inspection reports were requested and none provided.
2 | SWPPP not available onsite and its location is not posted. Nobody at site. Wrong ID# posted.
3 | Sediment was swept from the street into the gutter where it remains. It must be removed.
4 | BMPs -Silt fence not adequately embeded. Gaps in Silt fence. Silt fence inappropriate for concintrated flows so additional ponding required.
Yes
2.1 | Discharge off site? (Y/N) |  |  | Yes | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | n/a
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action