## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C18E075 |  | Project Name: |  | Sevano Place Subdivision | [5 empty] | NMR10039R & 39X | ckelsey@stillbrooke.com
NPDES Id. No. | NMR10039R/NMR10039X/NMR1003B0 |  | Location: |  | 6300 Alameda Blvd. NE | [5 empty] | Sevano Place Subdivision
2021-12-28 |  | Owner |  |  |  | owner & Contractor |  |  |  |  | 6300 Alameda Blvd NE | Joel Rodriguez
Operator |  | Sevano, LLC. |  |  |  | Stillbrooke Homes | [5 empty] | Stillbrooke Homes
Contact name & title |  | Shakeel Rizvi |  |  |  | Chris Kelsey |  |  |  |  | Sevano LLC & Clearbrook Investments | joelr@stillbrooke.com
e-mail |  | shaky1424@yahoo.com |  |  |  | ckelsey@stillbrooke.com |  |  |  |  | Shakeel Rizve & Chris Kelsey | 505-206-4456
Contact Phone # |  | 505-315-6563 |  |  |  | 505-858-1800
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 1pm |  |  |  | Rain
Construction Phase: |  | infrastructure | [9 empty] | Clear/ Windy
Type of Inspection: |  |  |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Cloudy |  | Temperature: ~ |  |  | 47 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-10-01 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | SWPPP map should not only identify the lots sold to Stillbrooke but also the finished occupied houses (3 or 4 now). Stillbrook's NOI (NMR1003UE) still missing from SWPPP | [9 empty] | 2021-05-03
2 | Concrete, paint, and stuco washout still on the ground. Provide more washouts containers and pickup existing washout.. | [9 empty] | 2021-05-31
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  |  | Latest report Date: |  | 2021-12-23
Notes: | one small common area 40' x 40' still needs stabilized by the developer.
Less than 10 housing starts .Most lots not yet sold to Stillbrook. Some have washout, presumably Stillbrook's doing and their responsibility to clean up.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | James D. Hughes 505-924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action