## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information | [10 empty] | Alto Rey, Agua Fria
ESC File No. | C18E085 |  | Project Name: |  | Allaso Olivine | [6 empty] | Angelica Saiz <angelica.saiz@pulte.com>
NPDES Id. No. | NMR10059X & '5CC |  | Location: |  | 6925 Alameda Blvd NE | [5 empty] | Kevin Patton | 505-604-4924
2024-10-07 |  | Owner |  |  |  | Contractor |  |  |  |  | 341-8591
Operator |  | Titan Olivine, LLC |  |  |  | HB
Contact name & title |  | Josh Rogers |  |  |  | Zach Gruen VP & Matthew Barnard SI
e-mail |  | jrogers@titan-development.com |  |  |  | zachg@Hbconstruction.com & leer@'
Contact Phone # |  | 505-998-0111 |  |  |  | 856-0404 & 250-2069
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 3pm |  |  |  |  | Rain
Construction Phase: |  | verticals/exteriors | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 85 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2024-07-22 |  |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Washout - The washout container had leaked and deposited on bare soil in violation of CGP Part 2.3.4. Required mitigation: Direct wash water into a leak-proof container or leak-proof and lined pit designed so no overflows can occur due to inadequate sizing or precipitation. Do not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground per CGP Part 2.3.4. | [9 empty] | 2021-05-03
2
3
2.1 | Discharge off site? (Y/N) |  |  | No | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2024-09-17
Notes:
The SWPPP is in the northern portion of the building (nearest to Oakland Ave)
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English 505-924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action