## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information | [10 empty] | Alto Rey, Agua Fria
ESC File No. | C18E085 |  | Project Name: |  | Allaso Olivine | [6 empty] | Angelica Saiz <angelica.saiz@pulte.com>
NPDES Id. No. | NMR10059X & '5CC |  | Location: |  | 6925 Alameda Blvd NE | [5 empty] | Kevin Patton | 505-604-4924
2025-03-06 |  | Owner |  |  |  | Contractor |  |  |  |  | 341-8591
Operator |  | Titan Olivine, LLC |  |  |  | HB
Contact name & title |  | Josh Rogers |  |  |  | Zach Gruen VP & Matthew Barnard SI
e-mail |  | jrogers@titan-development.com |  |  |  | zachg@Hbconstruction.com & leer@'
Contact Phone # |  | 505-998-0111 |  |  |  | 856-0404 & 250-2069
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 2pm |  |  |  |  | Rain
Construction Phase: |  | interiors, landscaping | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | cloudy |  | Temperature: ~ |  |  | 60 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-11-07 |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | The permit coverage was missing from the site perimeter in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site per CGP Part 1.5. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site, and it must use a font large enough to be readily viewed from a public right-of-way. | [9 empty] | 2021-05-03
2
3
2.1 | Discharge off site? (Y/N) |  |  | No | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2025-03-03
Notes:
The SWPPP is in Room 130
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English 505-924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action