## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C18E086 |  | Project Name: |  | Alameda Mixed-Use | [6 empty] | Gary Christensen
NPDES Id. No. | NMR1001U5 |  | Location: |  | 6100 Alameda NE | [5 empty] | Roy Solomon | 720-8475
2021-11-15 |  | Owner |  |  |  | Contractor
Operator |  | Green Jeans West, LLC. |  |  |  | Snyder Construction
Contact name & title |  | Roy Solomon |  |  |  | Terminated
e-mail |  | roy@roysolomon.org
Contact Phone # |  | 505-401-1000
COA Inspector |  | James Hughes |  |  |  | Start/End Time: |  | 11:30am |  |  |  |  | Rain
Construction Phase: |  | Stabilization/inactive | [10 empty] | Clear/ Windy
Type of Inspection: |  |  |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 58 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-10-01 |  |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Repair/replace downed silt fence on both East ends of the property, or Spread gravel stabilization. | [9 empty] | 2021-05-03
2 | SWPPP not up-to-date. Operator's signature missing from self-inspection reports. Operator didn't sign SWPPP. NOI missing from SWPPP (Tab 3 is empty). | [9 empty] | 2021-05-31
3 | Posting still includes Snyder's permit coverage which has been terminated. Delete Snyder from the sign.
4
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  |  | Latest report Date: |  | 2021-11-11
Notes: | There isn't a deligation of authority. Stabilization of east lot in progress.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | James Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action