## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C18E086C |  | Project Name: |  | Whataburger
NPDES Id. No. | NMR1005SZ |  | Location: |  | 6100 Alameda Blvd NE
2024-07-08 |  | Owner |  |  |  | Contractor
Operator |  | Whataburger |  |  |  | CKP Construction
Contact name & title |  | Abraham Vazquez |  |  |  | Todd Barbour
e-mail |  | avazquez@wbhq.com |  |  |  | tbarbour@ckpconstruction.com
Contact Phone # |  | 210-476-6614 |  |  |  | 806-420-0696
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 2pm |  |  |  | Rain
Construction Phase: |  | Verticals | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 90 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2024-06-30 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | The SWPPP has not been certified by both operators' signatories in violation of CGP Part 7.2.10. The self-inspection reports were not up-to-date in violation of CGP Part 4.7.3. Required mitigation: Your signatory must sign and date your SWPPP in accordance with Appendix G, Part G.11, as per CGP Part 7.2.10. You must keep a copy of all inspection reports at the site or at an easily accessible location, so that they can be made immediately available at the time of an on-site inspection per CGP Part 4.7.3.
2 | [10 empty] | 2021-05-03
3
2.1 | Discharge off site? (Y/N) |  |  | No | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2024-05-13
Notes:
The SWPPP was on-site in the construction office. The superintendent was not present at the time of inspection. The delegation of authority pages are filled out but not signed by the operators.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English 505-924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action