## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C18E087 |  | Project Name: |  | Precision Storage
NPDES Id. No. | NMR10073O |  | Location: |  | 6217 Signal Ave NE
2025-12-12 |  | Owner |  |  |  | Contractor
Operator |  | Precision Storage, LLC |  |  |  | Arbor Construction
Contact name & title |  | David Bedy |  |  |  | Kory Baker
e-mail |  | david@montanoacura.com |  |  |  | j.kory.baker@gmail.com
Contact Phone # |  | 505-280-7398 |  |  |  | 505-450-7517
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 9:30am |  |  |  | Rain
Construction Phase: |  | verticals | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 55 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-11-20 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | Washout - The concrete washout container has leaked and there is a separate area of bare ground that has washout in violation of CGP Part 2.3.4. Required mitigation: Direct wash water into a leak-proof container or leak-proof and lined pit designed so that no overflows can occur due to inadequate sizing or precipitation per CGP Part 2.3.4. Do not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2025-12-08
Notes:
SWPPP was in the mobile construction office. The superintendent had the inspection reports in his truck.
The superintendent is aware of the washout areas.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action