## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C18E088 |  | Project Name: |  | The Peaks by Markana Ph I
NPDES Id. No. | NMR1003VA & NMR1003VB |  | Location: |  | 6700 Modesto Avenue NE
2023-12-04 |  | Owner |  |  |  | Contractor
Operator |  | KLG 9, LLC. |  |  |  | Kasam Construction
Contact name & title |  | Faizel Kassam |  |  |  | Stephen Pendergraft
e-mail |  | fkassam@legacy-hospitality.com |  |  |  | Spendergraft@Legacydm.net
Contact Phone # |  | 505-489-4474 |  |  |  | 720-7188
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 11Am |  |  |  | Rain
Construction Phase: |  | Interior finish - 80% paved - 0% occupied | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Cloudy |  | Temperature: ~ |  |  | 45 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2023-11-19 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | none | [9 empty] | 2021-05-03
2 | [10 empty] | 2021-05-31
3 | [10 empty] | 2021-06-28
2.1 | Discharge off site? (Y/N) |  |  | No | [6 empty] | No
4 | Self Inspection Reports |  |  | ok | Latest report Date: |  | 2023-11-27
Notes:
All previous violations have been mitigated. The SWPPP is in the construction office in the middle south apartment. The sediment basin appears to be sized for the 2-yr storm, but the overflow isn't defined and may cause damage to neighboring property to the west. The west wall has many drain holes, but the G&D plan shows that the entire site is supposed to drain into the property to the south. The drain holes in the west wall are at the same elevation as the south driveway. Stephen Pendergraft added the pond to the SWPPP map, but his professional consultants should check the pond's design and safety.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action