## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
Project Name: |  | Alameda Crossing (f.k.a. Campo del Norte)
Location: | [5 empty] | ESC File No. |  | NPDES Id. No.
Site Contact Name & Agency |  | Chris Montoya - Pulte |  |  |  | Phone: (o)
|  | Christopher.Montoya@PulteGroup.com |  |  |  | Phone: (m) | 505-277-7727
Owner |  | Pulte Homes |  |  |  | Phone: (o)
Owner's e-mail | [5 empty] | Phone: (m)
Inspection Date: |  | 2020-09-11 | Start/End Time: |  | 0945/1030hrs | [6 empty] | Partly Cloudy
CoA Stormwater Inspector: |  |  | Timothy E. Sims | [8 empty] | Rain
Construction Phase: |  | home construction | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event |  | Post Storm Event >0.25" |  | 311/Complaint | x | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Partly Cloudy |  |  | Temperature: ~ |  | 57* |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2020-08-31 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Sediment BMP or stabilization of soil north of property line and curb line of Alameda
Yes
2.1 | Discharge off site? (Y/N) |  |  | No | [6 empty] | No
4 | Self Inspection Reports |  |  |  |  | Latest report Date:
Notes: | Inspection conducted adhering to Covid-19 constraints
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Timothy E. Sims - (505) 803-6155
|  | tsims@cabq.gov |  |  |  |  | 2020-09-11

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action