## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C18E102 |  | Project Name: |  | Alameda Crossing (f.k.a. Campo Del Norte) | [5 empty] | Alameda Crossing (f.k.a. Campo del Norte)
NPDES Id. No. | NMR1001LO |  | Location: |  | Alameda and San Mateo | [5 empty] | NMR1001LO
2021-06-15 |  | Owner |  |  |  | Contractor
Operator |  | Pulte Group |  |  |  | Pulte Group
Contact name & title |  | Christopher Montoya |  |  |  | Kevin Patton |  |  |  |  | 505-227-7727
e-mail |  | Christopher.Montoya@PulteGroup.com |  |  |  | Kevin.Patton@pultegroup.com |  |  |  |  | Christopher.Montoya@PulteGroup.com
Contact Phone # |  | 505-227-7727 |  |  |  | 505-908-4560
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 10:20 AM-10:30 AM |  |  |  | Rain
Construction Phase: |  | Stabilization | [9 empty] | Clear/ Windy
Type of Inspection: |  |  |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 85 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-05-31 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | No posting of NOI permit coverage. Post signage of NOI permit coverage in a location clearly visiible to the public. | [9 empty] | 2021-05-03
2 | Sediment in the street. Sweep and remove sediment that accumulates in the street. | [9 empty] | 2021-05-31
3 | Silt fences need maintenance. Repair/replace silt fences to prevent sediment from entering the street.
4 | Tract along Alameda is not stabilized per CGP 2.2.14.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2020-11-08
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action