## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
Project Name: |  |  | Alameda Crossing (Campo del Norte)
Location: |  |  | alameda and louisiana
Site Contact Name & Agency |  |  | Troy Crutchfield - Pulte |  |  |  | ESC File No. | C18E102
|  |  | troy.crutchfield2@pulte.com |  |  |  | NPDES Id. No. | NMR100LO
Inspection Date: |  |  | 2020-01-14 | Start/End Time: |  | 1210/1300hrs
CoA Stormwater Inspector: |  |  |  | Timothy E. Sims | [9 empty] | Rain
Construction Phase: |  |  | home construction | [10 empty] | Clear/ Windy
Type of Inspection: |  | x | Regular |  | Storm Event |  | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  |  | Clear |  |  | Temperature: ~ |  |  | 41* |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [9 empty] | 2020-11-27 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [13 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Please provide latest SWPPP self-inspection report.
2 | Concrte Washouts. Mitigate all illicit concrete washouts on site. Utilize provided concrete
washout facility.
3 | Inlet protection requires refreshing.
4 | Waste not in acceptable containers. Place all waste in an acceptable container.
5 | Sediment in street. Remove and prevent sediment from entering the street.
6 | Paint washout and overspray requires mitigation. Ensure trades utilize appropriate BMP to prevent
an issue.
Yes
2.1 | Discharge off site? (Y/N) |  |  |  | No | [7 empty] | No
4 | Self Inspection Reports |  |  |  | requested |  | Latest report Date: |  | 2019-09-02
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  |  | Timothy E. Sims - (505) 803-6155
|  |  | tsims@cabq.gov |  |  |  |  | 2020-01-14

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action