## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C18E108 |  | Project Name: |  | San Pedro Apartments
NPDES Id. No. | NMR10055P |  | Location: |  | 9320 San Pedro Dr NE
2024-10-07 |  | Owner |  |  |  | Contractor
Operator |  | GTA San Pedro LLC |  |  |  | Tekin Construction
Contact name & title |  | Mark Tekin |  |  |  | Carina Sanchez
e-mail |  | mark.tekin@tekindevelopment.com |  |  |  | csanchez@tekindevelopment.com
Contact Phone # | [5 empty] | 505-933-0476
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 245pm |  |  |  | Rain
Construction Phase: |  | verticals, 66% stabilized | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 85 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-07-22 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The SWPPP is not up-to-date. The SWPPP Map does not show the current conditions of the site in violation of CGP Part 7.4.1. The self-inspection reports were not current in violation of CGP Part 4.7.3. Required mitigation: You must modify your SWPPP, including the site maps, within 7 days whenever you make changes to your construction plans, stormwater controls, or other activities at your site that are no longer accurately reflected in your SWPPPP per CGP Part 7.4.1. You must keep a copy of all inspection reports at the site or at an easily accessible location, so that it can be made immediately available at the time of an on-site inspection per CGP Part 4.7.3.
2
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2024-03-11
Notes:
The SWPPP is located in Unit 2211. The current superintendents are not receiving the inspection reports.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English 505-924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action