## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
Project Name: |  |  | Rpohan Subdivision
Location: |  |  | Eagle Rock & Wyoming
Site Contact Name & Agency |  |  | Rich Ganter- tierra Homes |  |  |  | ESC File No. | C19E042A_T
|  |  | richganter@lobo.net |  |  |  | NPDES Id. No. | NMR1001V3
Inspection Date: |  |  | 2019-12-11 | Start/End Time: |  | 1155/1220hrs
CoA Stormwater Inspector: |  |  |  | Timothy E. Sims | [9 empty] | Rain
Construction Phase: |  |  | Home construction | [10 empty] | Clear/ Windy
Type of Inspection: |  | x | Regular |  | Storm Event |  | Post Storm Event >0.25" |  |  | 311/Complaint | x | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  |  | Clear |  |  | Temperature: ~ |  |  | 46* |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [9 empty] | 2019-11-27 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [13 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Too much sediment in street. Sweep and remove sediment from Street
2 | Provide NPDES posting. Posting must be visible from R.O.W.
3 | Silt fence requires repair or reinstallation.
4 | A sediment BMP is required for lots not stabilized. (completed houses)
5 | Washouts on the northern most lot requires mitigation.
6 | please provide latest SWPPP self-inspection report.
Yes
2.1 | Discharge off site? (Y/N) |  |  |  | No | [7 empty] | No
4 | Self Inspection Reports |  |  |  | requested |  | Latest report Date: |  | 2019-10-18
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  |  | Timothy E. Sims - (505) 803-6155
|  |  | tsims@cabq.gov |  |  |  |  | 2019-12-11

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action