## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C19E061 |  | Project Name: |  | Alameda and Louisiana Commercial Development |  |  |  |  | phillindborg@comcast.net
NPDES Id. No. | NMR10000P |  | Location: |  | 7000 Alameda Blvd.
2021-05-25 |  | Owner |  |  |  | Contractor |  |  |  | Cassandra Durkin
Operator |  | Boyhahn, LLC |  |  |  | Snyder Construction
Contact name & title |  | Phil Lindborg
e-mail |  | phillindborg@comcast.net
Contact Phone # |  | 505-450-4388
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: | 2:15 PM/2:20 PM |  |  |  | Rain
Construction Phase: |  | Stabilization | [8 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  | 82 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-05-03 |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [10 empty] | Fog
Item Number | Deficiency/ Corrective Action | [8 empty] | 2021-04-28
1 | None. | [8 empty] | 2021-05-03
2
3
4
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [5 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date:
Notes: | Posting still on site. Site has been mulched.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action