## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C19E066 |  | Project Name: |  | Luna Vita
NPDES Id. No. | NMR10028U |  | Location: |  | Luna Vita Ct.
2021-04-13 |  | Owner |  |  |  | Contractor
Operator |  | Clearbrook Investments
Contact name & title |  | Chris Kelsey
e-mail |  | ckelsey@stillbrooke.com
Contact Phone # |  | 505-858-1800
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 12:35 PM/12:45 PM |  |  |  | Rain
Construction Phase: |  | Vertical | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 59 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2021-02-22 |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | No posting of NPDES Permit
2 | Minor Trackout
3
4
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2020-08-24
Notes: | Only one home remains to be finished (8613 Luna Vita Ct.).
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action