## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
Project Name: |  |  | Amarand
Location: |  |  | 9100 Holly Ave NE |  |  |  | ESC File No. | C20E079 |  | NPDES Id. No. | NMR10025V
Site Contact Name & Agency |  |  | Xenia - Paaru |  |  |  | Phone: (o) | 505-307-1501
|  |  | si@paarugroup.com |  |  |  | Phone: (m)
Owner |  |  | Hemal Patel - Paaru Builders |  |  |  | Phone: (o) | 505-271-1288
Owner's e-mail |  |  | hemal@paarugroup.com |  |  |  | Phone: (m)
Inspection Date: |  |  | 2020-09-09 | Start/End Time: |  | 1030/1100hrs
CoA Stormwater Inspector: |  |  |  | Timothy E. Sims | [9 empty] | Rain
Construction Phase: |  |  | vertical | [10 empty] | Clear/ Windy
Type of Inspection: |  | x | Regular |  | Storm Event |  | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  |  | Cloudy |  |  | Temperature: ~ |  |  | 47* |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [9 empty] | 2020-07-25 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [13 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Rain guage not witnessed on site. Please clarify most recent rain fall on SWPPP reports and
provide rain guage for the project site.
2 | Trackout on Holly requires mirigation prior to end of day today. A follow up occurs tomorrow.
3 | Track out pad to site from Holly requires mitigation.
4 | Sediment in street requires mitigation. A follow up will occur tomorrow.
5 | Inlet BMP's require mitigation. Please provide inlet protection
6 | Sediment BMP's around the perimeter requires maintenance
7 | Washout on the NE corner of building (appears to have generated from 2nd floor window)
requires mitigation.
8 | Construction and domestic waste not in acceptable refuse location.
9 | Material storage of sheetrock and portland not protected from weather. Store in acceptable
location.
10 | Mitigate all concrete washouts on site.
Yes
2.1 | Discharge off site? (Y/N) |  |  |  | No | [7 empty] | No
4 | Self Inspection Reports | [5 empty] | Latest report Date: |  | 2020-09-08
Notes: | inspection conducted practicing safe social distancing
***All issues are noted on Contractor's provided SWPPP self-inspection report from "814"***
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  |  | Timothy E. Sims - (505) 803-6155
|  |  | tsims@cabq.gov |  |  |  |  | 2020-09-09

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action