## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C20E079 |  | Project Name: |  | Holly Senior Living / Amaran Senior Living
NPDES Id. No. | NMR10025V |  | Location: |  | 9100 Holly
2020-09-21 |  | Property Owner |  |  |  | Contractor
Operator |  | Mark11s, LLC |  |  |  | Paaru Group
Contact name & title | [5 empty] | Mike Hart, SI
si@paarugroup.com
Contact Phone # | [5 empty] | m 410-6578 o 271-1288
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 2:30-3:30PM |  |  |  | Rain
Construction Phase: |  | Vertical | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 76 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [11 empty] | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | BMPs - Hole in Silt fence. Construction entrance missing.
2 | Washout
3 | Construction and domestic waste
4 | the SWQ Team was not identified in the SWPPP
Yes
2.1 | Discharge off site? (Y/N) |  |  | No | [6 empty] | No
4 | Self Inspection Reports |  |  |  | Latest report Date: |  | 2020-09-21
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action