## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C20E086 |  | Project Name: |  | Allaso Vineyards
NPDES Id. No. | NMR1004EO |  | Location: |  | 8945 Holly Ave NE
2024-03-25 |  | Owner |  |  |  | Contractor
Operator |  | Titan Property Management |  |  |  | HB Construction
Contact name & title |  | Brian Patterson |  |  |  | Lee Riley
e-mail |  | bpatterson@titan-development.com |  |  |  | leer@hbconstruction.com
Contact Phone # |  | 505-998-0163 |  |  |  | 250-2069
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 10:45 |  |  |  | Rain
Construction Phase: |  | Interior Finish, Paving and Landscaping | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 45 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2024-03-16 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | NOI - Permit coverage expired | [9 empty] | 2021-05-03
2
3
4
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | OK | Latest report Date: |  | 2024-03-17
Notes: | SWPPP in west end 2nd floor
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action