## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C20E089 |  | Project Name: |  | Valentino Estates
NPDES Id. No. | NMR1006MK |  | Location: |  | 9200 Wilshire Ave NE
2025-06-17 |  | Owner |  |  |  | Contractor
Operator |  | Clearbrook Investments, Inc. |  |  |  | Stillbrooke Homes, Inc.
Contact name & title |  | Chris Kelsey
e-mail |  | ckelsey.clearbrook@stillbrooke.com
Contact Phone # |  | 505-858-1800
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 12:30pm |  |  |  | Rain
Construction Phase: |  | Sidewalks/WO | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 95 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-06-02 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | BMPs - The stabilized construction entrance appears to have been removed and needs replacement in violation of CGP Part 2.1.4. Required mitigation: Ensure all stormwater controls are maintained and remain in effective operating condition during permit coverage and are protected from activities that would reduce their effectiveness per CGP Part 2.1.4.
2 | Washout - There is no washout container or pit and an area of washout on bare soil near waste piles in violation of CGP Part 2.3.4. Required mitigation: Direct wash water into a leak-proof container or leak-proof and lined pit designed so no overflows can occur due to inadequate sizing or precipitation per CGP Part 2.3.4. Do not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | yes | Latest report Date: |  | 2025-06-09
Notes:
Only the SWPPP Map was attached to the back of the CGP Posting in a medicine cabinet.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action