## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C20E089 |  | Project Name: |  | Valentino Estates
NPDES Id. No. | NMR1006MK |  | Location: |  | 9200 Wilshire Ave NE
2025-11-10 |  | Owner |  |  |  | Contractor
Operator |  | Clearbrook Investments, Inc. |  |  |  | Stillbrooke Homes, Inc.
Contact name & title |  | Chris Kelsey
e-mail |  | ckelsey.clearbrook@stillbrooke.com
Contact Phone # |  | 505-858-1800
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 11:45am |  |  |  | Rain
Construction Phase: |  | Inactive, paving complete | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 60 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-10-14 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | None
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | ok | Latest report Date: |  | 2025-10-06
Notes:
Only the SWPPP Map was attached to the back of the CGP Posting in a medicine cabinet.
When pulling on-site for the inspection, a concrete truck had just finished washing out the chutes onto the bare soil of your property. Since washout has been a repeated violation, it is suggested that you take security measures to prevent contractors unrelated to your site from using your site for their disposal purposes while the site is inactive and unmanned.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action