## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | D09E005 |  | Project Name: |  | Montecito Vistas | [5 empty] | Dan Mallak | dan.mallak@pultegroup.com |  | Christopher Montoya (Construction) <Christopher.Montoya@PulteGroup.com>
NPDES Id. No. | NMR100BZ |  | Location: |  | Vista Vieja and Quivara Rd.
2021-05-13 |  | Owner |  |  |  | Contractor |  |  |  |  | Kevin Patton | Kevin.Patton@PulteGroup.com |  | Brian Anderson <brian.anderson@pultegroup.com>
Operator |  | Pulte Homes
Contact name & title |  | Kevin Patton |  |  |  | Troy Crutchfield |  |  |  |  | Tim Slatunas
e-mail |  | Kevin.Patton@Pultegroup.com |  |  |  | Troy.Crutchfield2@pulte.com
Contact Phone # |  | 505-238-2857 | [8 empty] | Troy Crutchfield | Troy Crutchfield <Troy.Crutchfield2@pulte.com>
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 1:20 PM/1:40 PM |  |  |  |  | Rain
Construction Phase: |  | Stabilization | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 78 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-05-03 |  |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Identify stabilization controls | [9 empty] | 2021-05-03
2
3
4
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2020-03-16
Notes: | Homes and HOA tracts are completed. Areas on the West and South sides remain
disturbed.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action