## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | D09E006 |  | Project Name: |  | Twilight at Quivera Estates
NPDES Id. No. | NMR1004B0 |  | Location: |  | 6700 Quivera Dr. NW
2025-09-10 |  | Owner |  |  |  | Contractor
Operator |  | Quivera Land, LLC |  |  |  | Twilight Homes
Contact name & title |  | Tim McNaney |  |  |  | Tim McNaney
e-mail |  | tmcnaney@twilighthomes.com |  |  |  | tmcnaney@twilighthomes.com
Contact Phone # |  | 322-6027 |  |  |  | 322-6027
COA Inspector |  | Chancellor English | [5 empty] | 9am |  |  |  | Rain
Construction Phase: |  | verticals, several houses complete | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 80 |  |  | Cloudy
[8 empty] | 2025-09-10 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The SWPPP Map needs to be brought up-to-date to reflect the transfer of properties to Abrazo Homes and Twilight Homes per CGP Part 7.4.1. The 2017 CGP needs to be replaced by the 2022 CGP in the SWPPP in violation of CGP Part 7.2.11. The most current inspection report was dated over a month ago in violation of CGP Part 4.7.3. Required mitigation: You must modify your SWPPP, including the site map(s) to reflect areas on your site map where operational control has been transferred (and the date of transfer) since initiating permit coverage per CGP Part 7.4.1.b. You must include a copy of the 2022 Construction General Permit in the SWPPP per CGP Part 7.2.11. You must keep a copy of all inspection reports at the site or at an easily accessible location so that they can be made immediately available at the time of an on-site inspection per CGP Part 4.7.3.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2025-07-21
Notes:
The SWPPP and inspection reports are in a doc-box mounted on the back of the positing. The pond needs to be stabilized.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English 505-924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action