## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | D10E002B |  | Project Name: |  | La Cuentista II | [5 empty] | Kevin T Griffin <KTGriffin@drhorton.com>
NPDES Id. No. | NMR1001S6/NMR1000HM |  | Location: |  | 8212 Burdock
2021-06-21 |  | Owner |  |  |  | Contractor |  |  |  |  | Gary Illingworth
Operator |  | Double M Properties |  |  |  | D.R. Horton |  |  |  |  | La Cuentista Units 1 & 2 HOAs
Contact name & title |  | Bob Prewitt |  |  |  | Kevin Griffin |  |  |  |  | Gillingworth@hoamco.com
e-mail |  | prewitt@swcp.com |  |  |  | KTGriffin@drhorton.com
Contact Phone # | [5 empty] | 505-206-8227
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 11:45 AM-11:50 AM |  |  |  | Rain
Construction Phase: |  | Vertical | [9 empty] | Clear/ Windy
Type of Inspection: |  |  |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 86 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-05-31 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Washout on the ground. Place wash water from concrete, paint, and stucco into a leak-proof container. | [9 empty] | 2021-05-03
2 | Provide latest self-inspection report. | [9 empty] | 2021-05-31
3 | HOA tracts are not stabilized.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2020-07-30
Notes: | One home remains to be finished.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action