## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | D10E002D |  | Project Name: |  | La Cuentista III
NPDES Id. No. | NMR1004P9 |  | Location: |  | Rosa Parks and Kimmick
2024-04-26 |  | Owner |  |  |  | Contractor
Operator |  | Pulte Homes of NM |  |  |  | Guzman
Contact name & title |  | Kevin Patton |  |  |  | Rudy Guzman
e-mail |  | kevin.patton@pultegroup.com |  |  |  | rudy@guzmancs.com
Contact Phone # |  | 505-341-8591 |  |  |  | 505-459-3128
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 12pm |  |  |  | Rain
Construction Phase: |  | verticals | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 70 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-04-01 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | SWPPP - The Inspection Reports were signed by a representative for Pulte Homes. The signed Delegation of Authority does not name an individual or position in violation of CGP Appendix G, Section G.11.2. Complete the Delegation of Authority page to assign Cody Watson (or stormwater representative) to sign Inspection Reports for Pulte Homes according to CGP Appendix G, Section G.11.2.2.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2024-03-27
Notes:
The construction entrance on Azucena Pl has sediment build-up that should be cleared.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action