## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | D10E002D |  | Project Name: |  | La Cuentiasta III & Stockpile
NPDES Id. No. | NMR1004P9 |  | Location: |  | Rosa Parks and Kimmick
2022-08-09 |  | Owner |  |  |  | Contractor
Operator |  | Pulte Homes of NM |  |  |  | Guzman Construction
Contact name & title |  | Kevin Patten |  |  |  | Rudy Guzman
e-mail |  | Kevin.Patton@PulteGroup.com |  |  |  | rudy@guzmancs.com
Contact Phone # |  | 505-341-8591 |  |  |  | 505-459-3128
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 13:15 |  |  |  | Rain
Construction Phase: |  | Staging | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 96 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2022-07-24 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | A separate SWPPP and NOIs were approved by the City for the Rosa Parks Stockpile Yard (see file C11E004 and NMR1004ZB, NMR100501 and NMR100504) | [9 empty] | 2021-05-03
2 | Current self-inspection reports were missing from the onsite SWPPP for La Cuentista III. | [9 empty] | 2021-05-31
3 | [10 empty] | 2021-06-28
4 | [10 empty] | 2021-07-06
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2022-07-07
Notes:
The SWPPP is in the lockbox on Pulte's posting sign at the SW corner of the site.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action