## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | D16E002H |  | Project Name: |  | Apple Canyon Gourmet | [6 empty] | Brad Frosch (bfrosch@tierrawestllc.com)
NPDES Id. No. | NMR10048T |  | Location: |  | 1301 Cuesta Abajo Ct NE | [8 empty] | Zeke Mares <Zeke.Mares@feinm.com>
2023-04-10 |  | Owner |  |  |  | Contractor | [5 empty] | abrunacini@brunacini.com
Operator |  | Cloche, LLC |  |  |  | Mickrich contractors | [7 empty] | Jesus Jurado <Jesus.Jurado@feinm.com>
Contact name & title |  | Greg Shawver |  |  |  | Jim Rich | [5 empty] | gary.huffman@feinm.com
e-mail |  | Greg@applecanyon.com |  |  |  | Jim@mickrichcontractors.com | [7 empty] | VCarrica@tierrawestllc.com
Contact Phone # |  | 332-2000 |  |  |  | 823-9782 | [5 empty] | John Ellis <John.Ellis@feinm.com>
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 2pm |  |  |  |  | Rain |  | Gus.Harbaugh@feinm.com
Construction Phase: |  | Stabilization | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy |  | vperea@tierrawestllc.com
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 78 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2023-03-16 |  |  |  |  | 2021-02-22 |  | Sleet |  | Brad.Graham@feinm.com
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [13 empty] | gary.huffman@feinm.com
1 | Permit coverage wasn't posted. You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site, and it must use a font large enough to be readily viewed from a public right-of- way per CGP 1.5
2 | The SWPPP including Self Inspection Reports and Corrective Action Reports must be kept up-to-date per CGP 7.1 and available on-site per CGP 4.7.3, 5.4.3 and 7.3. If an on-site location is unavailable to keep the SWPPP when no personnel are present, notice of the plan’s location must be posted near the main entrance of your construction site CGP 7.3. Provide a copy of the latest self inspection report.
3 | Rear yard doesn't satisfy CGP2.2.14.c Final Stabilization Criteria, but it has been seeded and mulched per CGP2.2.14, and new grass is growing. Soil is very gravelly and rocks provide significant cover.- You must continue permit coverage, self-inspections, SWPPP and BMP maintenance until the City determines that the Final Stabilization Criteria CGP2.2.14.c has been satisfied. Then you must send documentation of the Final Stabilization to the EPA with a Notice of Termination (NOT) per CGP 8.2 to end your coverage under the CGP. This step is independent of the Certificate of Occupancy. Please copy me with the documentation and the EPA’s acceptance of the NOT.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | ?
Notes: | Building is occupied and open for business.
CGP Coverage NMR10048T is "Active"
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action