## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | D16E104 |  | Project Name: |  | Cuesta Arriba Warehouse
NPDES Id. No. | NMR1006E0 |  | Location: |  | 1320 Cuesta Arriba Ct NE
2025-01-15 |  | Owner |  |  |  | Contractor
Operator |  | Groff Limited Partnership |  |  |  | Insight Construction, LLC
Contact name & title |  | Lara Groff |  |  |  | Dave Brown
e-mail |  | grofflp@gmail.com |  |  |  | dave@insightnm.com
Contact Phone # |  | 505-379-0236 |  |  |  | 505-888-7927
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 11am |  |  |  | Rain
Construction Phase: |  | Verticals | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 45 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-11-07 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | SWPPP - The SWPPP has not been certified by either operator in violation of CGP Part 7.2.10. The self-inspection reports were unavailable for the inspection in violation of CGP Part 4.7.3. Required mitigation: Your signatory must sign and date your SWPPP in accordance with CGP Appendix G, Part G.11 per CGP Part 7.2.10. You must keep a copy of all inspection reports at the site or at an easily accessible location so that they can be made immediately available at the time of an on-site inspection per CGP Part 4.7.3.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
Delegation of Authority: The SWPPP certification and the inspection reports can be signed by an authorized representative for each operator, as long as the Delegation of Authority pages are properly completed and signed by the operators' NOI certifier. The delegation cannot be to a third party, therefore the pages with Inspections Plus listed as a signatory are inadmissible by EPA rules. Please see CGP Appendix G, Part G.11.2 for admissible authorized representatives.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action