## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | D17E003A |  | Project Name: |  | Cottonwood Classical Academy
NPDES Id. No. | NMR1004DU |  | Location: |  | 7800 Jefferson St NE
2023-06-13 |  | Owner |  |  |  | Contractor
Operator |  | Cottonwood Classical Foundation |  |  |  | Inspections Plus
Contact name & title |  | John Binnert
e-mail |  | john.binnert@cottonwoodclassical.org
Contact Phone # |  | 505-998-1021 |  |  |  | 505-344-9410
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: | 2 |  |  |  | Rain
Construction Phase: |  | infrastructure complete | [8 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  | 80 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [6 empty] | 2023-05-22 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [10 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The NOI coverage expired in February of 2022. Construction activities seems to have ceased, but, according to the 2022 CGP Section 8, you must comply with the conditions of the permit until you terminate coverage. File for NOT if one ore more of the conditions in CGP Section 8.2.1, 8.2.2, or 8.2.3 are satisfied.
2 | The required NPDES posting was missing/removed. While under CGP coverage, you must comply with the conditions of the permit. Section 1.5 of the CGP requires that you must post a sign or notice of NPDES coverage in a safe, publicly accessible location.
3 | There was no SWPPP available during the time of inspection. While under CGP coverage, you must comply with the permit. Secion 7.1 states that you must develop and update a SWPPP throughout coverage and ensure that it meets the current 2022 CGP requirements. Section 7.3 states that you are required to keep a current copy of the SWPPP on-site or easily accesible so that it can be made available for inspections.
4 | BMPs were not installed and the land has not been stabilized. While under CGP coverage, you must comply with the permit. In accordance with CGP Sections 2.2.3 and 2.2.6, you must install sediment controls along any perimeter areas of the site that are downslope form any exposed soil or other disturbed areas and you must minimized dust by the appropriate application of water or other dust suppression techniques. Fully surrounding the disturbed areas with the proper sediment controls would satisfy both requirements
5 | Construction work seems to have ceased and the site is inactive. Section 2.2.14 requires you to immediately initiate of stabilization measures for areas where construction activities have permanently ceased or will be temporarily inactive for 14 or more calendar days. If construction operations have ceased, disturbed areas need to be stabilized according to Sections 2.2.14.c and file for NOT to terminate coverage after satisfiying conditions in Section 8.2.
In accordance with City Ordinance § 14-5-2-11(C)(1), self-inspections must continue until the site is “determined as stabilized by the city.” The property owner/operator is responsible for determining when the “Conditions for Terminating CGP Coverage” per CGP Part 8.2 are satisfied and then for filing their Notice of Termination (NOT) with the EPA. Each operator may terminate CGP coverage only if one or more of the conditions in Part 8.2.1, 8.2.2, or 8.2.3 has occurred. After filing the NOT with the EPA, the property owner is responsible for requesting a Determination of Stabilization from the City.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [5 empty] | No
4 | Self Inspection Reports |  |  | no | Latest report Date:
Notes: | No prior inspections performed, construction activity seems to have ceased and all BMPs
have been removed. There are still stockpiles and distrubed land that are not stabilized. The NOI
is expired.
| City of Albuquerque Stormwater Inspector Signature and date: | [5 empty] | 2023-06-16
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action